## Project 3 timeline
Milestone | Date | Responsible
Define scope and timeline | 2024-12-17 | All
Definition of data base and scope | 2024-12-17 | Ingrid and Jen
Creation Git hub | 2024-12-18 | Ingrid
Geography check out if we have info? | 2024-12-18 | Jen and Dhanielle
What can we create in Java/HTML? | 2024-12-18 | Jen and Dhanielle
Review the Html | 2024-12-20 21:00 | Dhanielle
Data Base Clean up | 2024-12-20 | Dhanielle
Create SQL Database | 2024-12-23 | Ingrid C
Run Analysis | 23-26
Categories: Tech, Grocery, Home Decor, Books, Clothing |  | Ingrid C
DeepDive: Tech
Split of sales per Category sales (pie) |  | Ingrid C
Split per Brands |  | Ingrid C
Split sales Price |  | Jen
Split per Customer Age |  | Dhanielle
Split Customer Gender |  | Ingrid C
Split Customer income |  | Dhanielle
Correlations Brands vs. Age |  | Ingrid C
Correlations Brands vs. Gender |  | Jen
Correlations Categories vs. Gender & age |  | Dhanielle
Correlations Price vs. Age |  | Dhanielle
Correlations customer satisfaction vs. Brand |  | Ingrid C
Correlations Customer satisfaction vs. Purchase |  | Ingrid C
Correlation season (date) products sold |  | Jen
Correlation valentines men purchases |  | Jen
Correlation Income, gender and purchases |  | Jen
Correlation Geography and income |  | Dhanielle
Maps
Geomap: Heat map: Category focus and correlation in Tech (intro) |  | Jen
Geomap: Heat map: Subcategory tech |  | Jen
Geomap: Heat map: Gender and Purchases $ |  | Jen
first Check in | 9:00pm 26th
Second Check in | 27th
Last check in: Consolidation in the system | 2024-12-30
Prepare presentation | 2024-01-02 | Challenges | Post analysis to be done
Create JavaScript
Create Html | 2024-01-02
Conclude Presention | 2025-01-06
Presentation to Krystyna | 2025-01-08